## Sheet1
general progress till previous week (till now completed with simulink model and rough trajectory for leg)
ashutosh | kinematic modelling, simulation on simulink, made simulink model, trajectory planning, basics of dynamics (E-L method)
yash |  | Reminders
pranav | kinematic modelling, simulation on simulink, trajectory planning,basics on dynamics,robotic system toolbox model | 14th September nptel course start
abdul | kinematic modelling, simulation on simulink, made simulink model, trajectory planning, basics of dynamics (E-L method) | 2nd august sandbox submission
paurush
vedang
ashita
week 0 (dynamics)
ashutosh | Read and understood about tree type robotic system representation - Kinematic model, Dynamic equations (DeNOC N-E)
yash
pranav | applying euler lagrange on quadrapued,learning to calculate wrench
abdul
vedang
parush
ashita
week 1 07/07 - 14/07 (starting to calculate required matrices and parameters for the quadrapued and working on denoc NE)
ashutosh | Understood chapters 4-5 of tree type robotic systems book completely
yash
pranav | trying to figure out wrench using spatial forces contact
abdul | Began reading up on tree type robotic systems. Learnt about recursive dynamics and further understood inverse and forward kynematics
vedang
parush | went through tree type robot dynamics chapters
ashita
week 2 14/07 - 21/07
ashutosh | Corrected the model to represent correct frames and found some matrices
yash
pranav | figured out calculating wrench, for the last link. trying to find a general method for all link
abdul | tried to draw out similarites between old hexapod simulink models and the rotation matrices given in the book
vedang
parush | continued with chapter 4 and chapter 5 of the book
ashita
week 3 21/07 - 28/07
ashutosh | Clarified the basics from the Modern robotics book
yash | completed the tille chapter 4 not able to understand wrench calculations -- hung up in chapter 5
pranav
abdul | Studied up the models and matrices in chapters 4 & 5/ Worked on the Simulink leg models of the old Hexapod and tried to modify the transformation matrix in base joint
vedang
parush
ashita
week 4 28/07 - 04/08
ashutosh | Modern robotics book until chapter 5
yash | started more into chater 5 read the papers in ideas // will start working on matlab model soon // take 2-3 days to understand moredern robotics book
pranav
abdul
vedang
parush
ashita